## Slide 1: CMX: tasks and schedule
Wojtek Fedorko for the MSU group

## Slide 2: CMX development schedule as shown before (still valid)
2011: Project and engineering specifications
  CMX project Preliminary Design Review (Done)
  Preliminary design studies (Ongoing)
  Test rig installed, checked out at MSU (postponed until 2012)
2012: Prototype design and fabrication
  CMX schematics and PCB layout (ongoing)
  CMM firmware ported on CMX
  Prototype fabrication (fall 2012)
  Basic tests for backward compatibility in test rig at MSU
  Production Readiness Review
2013: Prototype testing/installation/commissioning, final fabrication
  Full prototype tests in test rig at CERN
  CMX firmware development and test
  Test in the L1Calo system during shutdown
  Fabricate and assemble full set of CMX modules
2014: Final commissioning in the L1Calo trigger system in USA15
Notes: 1

## Slide 3: CMX development timeline: Yuri’s/Dan’s slide from mini-TDAQ
Notes: 2

## Slide 4: Hardware milestones
Preliminary Design Review (PDR): - Stockholm
Final Design Review (FDR)
  Not included in the scheduled discussed previously
  Required procedure?
  If required best option would be to have FDR after design sent for fabrication
prototype: 2013.01.31
Production Readiness Review (PRR):
  After prototype received and tested
production: ~fall 2013
installation: ~spring 2014

## Slide 5: Firmware development planning

## Slide 6: Slide from Sam’s May 24th talk
“MSU will develop format-independent
boundaries to the FPGAs on the CMX,
and coordinate subsystem-specific code development with other institutes."

## Slide 7: Base CMX Firmware versions: from Sam’s May 24th talk
*
*
* continued development by Wojtek at UBC
*
*
* no firm commitment from MSU (except for coordination)

## Slide 8: Base CMX Firmware – filling in the boxes (system)
Input module
decoder
LVDS RX
MGT TX
L1 Topo output block
CMM emulator
Crate
System
glink emulator
LVDS TX
LVDS @160Mbps
Backplane 16x24x160Mbps
To CTP LVDS @40Mbps
To L1Topo
6.4Gbps
16x96x40Mbps
readout
VME config/control
Common to all flavors
Flavor specific
Legend:

## Slide 9: Base CMX Firmware – filling in the boxes (crate)
Input module
decoder
LVDS TX
MGT TX
L1 Topo output block
CMM emulator
Crate
System
glink emulator
LVDS TX
LVDS @160Mbps
Backplane 16x24x160Mbps
To CTP LVDS @40Mbps
To L1Topo
6.4Gbps
16x96x40Mbps
readout
VME config/control
Common to all flavors
Flavor specific
Legend:

## Slide 10: Input Module
Was needed urgently to guide layout
Implemented with the clk/parity encoding scheme
  Will be tested in eval kit
First implementation with 80 MHz DDR scheme
  Needs verification and eval kit test
In both cases ‘toy’ interface
  Full projected functionality
    e.g. IDELAY, IDDR
    details of how this would be configured will change
  Capture data into registers and ‘deserialization’ into 96 bit word
  No synchronization between channels
Parity calculation and error flag

## Slide 11: Other Firmware Modules
Need to define functionality and interfaces between firmware ‘modules’
Resource sharing (e.g. MMCM – clock generation and buffering)
‘Take out’ some functionality from the CMM emulator module
Start work from the ‘Jet’ version of CMX
  Expect that common module interfaces will work for other versions
  Manpower (Pawel) available to work on this version outside of MSU
    Experience with CMM
  Will be able to use this or stripped down version of this firmware for board tests
  Need complete firmware before prototype arrives early next year. Hope ready sooner.
  Part of firmware testable in Yuri’s TTC/VME/ACE test card.
  Expect duty cycle between Pawel and myself to decrease in the coming weeks.
  Other firmware versions will follow after prototype tests.

## Slide 12: Questions that need clarification to guide the firmware design
80MHz DDR on bit 24 decided?
  Do we have an agreement on data formats for all flavors?
  Circulation of documentation?
Location of parity bit
  Constant in the payload between the flavors?
Synchronization of processor inputs
  At which stage this needs to happen? Input module?
Efficient use of the data format
  What data can be made available early to minimize latency?
Behavior on error?
  Include information in the real time data?
  Special L1A to force readout?
…

## Slide 13: CMX Topo FPGA
Plans for firmware development need to be discussed
Hope for common firmware architecture with L1Topo
Test version needs to be ready for prototype testing.
  Link tests

## Slide 14: Software development (Seth Caughron)
Goals:
  Ability to test the VME/TTC/ACE test card and CMX within L1Calo software framework
  Develop expertise now using the 6U crate in bldg. 32 and Yuri’s test card
  When prototype arrives we must be ready to test it.
Status:
  We need and are getting help
  Murrough and Seth have cloned the software objects modeling the CMM into CMX
    Assumes CMX register model will be an evolution of the CMM
  Working on setting up a small partition in the 6U crate
  Will be ‘playing’ with Yuri’s card on completion of the inspection and smoke test (mid August)

## Slide 15: Conclusions
Hardware schedule well defined
  Procedural question about FDR
Base CMX firmware goals set
  Most urgent tasks guiding hardware design complete
  Need finer planning of further development and more intermediate goals
TP-CMX firmware needs more thinking
Software work just starting
  Discussion in this forum very welcome
  We are grateful for the expertise provided so far (and we’ll need more)