## Slide 1
Status and planning of the CMX
Wojtek Fedorko for the MSU group
TDAQ Week, CERN
April 23 - 27, 2012

## Slide 2: CMX: CMM upgrade
Will replace CMM:
  Backplane rate 40 →160Mbs
  Crate to system rate (LVDS) 40 →160Mbs
  Cluster information sent to Topological Processor (optical)
  Optional partial TP functionality
    Standalone TP is now planned
    Some TP capability also designed onto the CMX

## Slide 3: CMX: Use scenario with standalone TP
Electron
Energy
Jet
Tau
Base-
CMX
FPGA
to CTP
LVDS
Cables
to CTP
to CTP
to CTP
Base-
CMX
FPGA
Base-
CMX
FPGA
Base-
CMX
FPGA
Base-
CMX
FPGA
Base-
CMX
FPGA
Base-
CMX
FPGA
Base-
CMX
FPGA
Base-
CMX
FPGA
Base-
CMX
FPGA
Base-
CMX
FPGA
Base-
CMX
FPGA
LVDS
Cables
LVDS
Cables
LVDS
Cables
Optical
Patch
Panel
Crate
CMXs
System
CMXs
- - - - - - - -
to CTP
Standalone
Topological
Processor
N x 12
12 x 12-fiber ribbons
12
1 x 12-fiber ribbon

## Slide 4: The CMX overview
VME-- Interface
TP-CMX FPGA
Virtex-6
LX550T-FF1759
Base-CMX FPGA
Virtex-6
LX550T-FF1759
12x Optic OUT
12x Optic OUT
12x Optic IN
12x Optic IN
12x Optic IN
DAQ
ROI
DAQ
ROI
TCM Interface
VME--
TCM
Inputs from all
JEM or CPM
processors
from this crate
LVDS cables
From Crate
To System CMX
400 single ended
@ 160Mbps
3x27 LVDS pairs
@ up to 160 Mbps
2x 12-fiber
ribbons OUT
3x 12-fiber
ribbons IN
6.4 Gbps outputs
to Standalone TP
and/or TP-CMX
2x G-Link Out
2x G-Link Out
6.4 Gbps inputs
re-bundled from
up to 12 Base-CMX
CTP output
2x33 LVDS pairs
@ 40 Mbps
(from TP-CMX
via Base-CMX)

## Slide 5: CMX: modular design, most cards assembled without TP functionality
VME-- Interface
Base-CMX FPGA
Virtex-6
LX550T-FF1759
12x Optic OUT
12x Optic OUT
DAQ
ROI
TCM Interface
VME--
TCM
Inputs from all
JEM or CPM
processors
from this crate
LVDS cables
From Crate
To System CMX
400 single ended
@ 160Mbps
3x27 LVDS pairs
@ up to 160 Mbps
2x 12-fiber
ribbons OUT
6.4 Gbps outputs
to Standalone TP
and/or TP-CMX
2x G-Link Out
CTP output
2x33 LVDS pairs
@ 40 Mbps
(System CMX
only)

## Slide 6: CMX development work on 3 fronts
Engineering @MSU
  Philippe, Dan, and Chip
CMX input module firmware @CERN
  Wojtek and Yuri
VME/ACE/TTC (VAT) interface @CERN
  Yuri
Request from Chris and David - to address and present:
"The detailed timeline & schedule from now until completion of commissioning at Point 1 in 2014 and a set of milestones associated to this schedule - typically ~10, including details of review procedure"
Initial CMX development schedule is still valid
  Minor adjustments
Notes: 5

## Slide 7: Initial CMX development schedule from 2011
2011: Project and engineering specifications
  CMX project Preliminary Design Review (Done)
  Preliminary design studies
  Test rig installed, checked out at MSU (postponed until 2012)
2012: Prototype design and fabrication
  CMX schematics and PCB layout
  Production Readiness Review
  Prototype fabrication, CMM firmware ported on CMX
  Basic tests for backward compatibility in test rig at MSU
2013: Prototype testing/installation/commissioning, final fabrication
  Full prototype tests in test rig at CERN
  CMX firmware development and test
  Test in the L1Calo system during shutdown
  Fabricate and assemble full set of CMX modules
2014: Final commissioning in the L1Calo trigger system in USA15
https://indico.cern.ch/getFile.py/access?contribId=31&sessionId=6&resId=0&materialId=slides&confId=152943
Notes: 6

## Slide 8: 2012
2012: Prototype design and fabrication
  CMX schematics and PCB layout
    CMX technology choice (FPGA choice, CMX/TP functionality) - DONE
    6U VME test card for VAT interface – PCB ready for testing in June
    Real-time data path layout (ongoing)
    CMX input module firmware currently under test on the XILINX development module
    Power budget estimate
  Prototype fabrication
    mechanical testing in January
      Will happen within ~month, not urgent yet.
      Blank card, backplane connectors, front panel tests.
  CMM firmware ported on CMX
    Firmware for VAT interface (2 CPLD + TTC FPGA) to Spartan-3AN FPGA (Adapt VHDL code, create test bench, specify VME register model) (Yuri)
    Most of the work completed at Stockholm (Pawel Plucinski, Sam Silverstein)
      Needs to be adapted to final package choice
  Basic tests for backward compatibility in test rig at MSU
  Production Readiness Review (L1Calo/TDAQ) Fall/Winter
    PRR after the prototype(s) is tested and
    final check before going into full production
Notes: 7

## Slide 9: 2011/2012: design studies: Clock/parity recovery
Clock+Parity encoded on single line
Variable duty cycle
Setup:
Scheme tested using Virtex 6 eval board
Data capture developed, simulated and ‘Placed and Routed’ on target FPGA
  Needs repeating – different package chosen
Clock/parity
Regional clock buffer (BUFR)
MMCM
Data
40 MHz
BUFR
80 MHz
BUFIO
IDDR
40MHz register
96 bits @ 40MHz
x 16

## Slide 10
2012: PCB layout: VME/ACE/TTC (VAT) interface test card
VME/ACE/TTC (VAT) part of CMM
Redesign HW with new components
    Fit design into single device
6U VME test card for
  Hardware implementation
  Main FPGA re-configuration
  Software
  To be merged into CMX design
PCB arrives in June
Next:
  Firmware for VAT card
  Firmware for Virtex 6 FPGA
  Test Stand and software
VME CPLD
TTC FPGA
ACE CPLD
SystemACE
TTCrx
FC
TTCDec
Spartan-3AN
VME-- logic
CF
SystemACE
JTAG
TTC
Connector for CANbus i/f
Virtex6
Power
5V0
3V3
2V5
1V0
3V3
2V5
1V0
1V2

## Slide 11: 2012 PCB Layout: Backplane – FPGA connection
Challenging milestone
  Signal density
  Avoid contention
Drives FPGA package choice
Implications for Firmware design
NOT FINAL

## Slide 12: 2013
2013: Prototype testing/installation/commissioning, final fabrication
  Full prototype tests in test rig at CERN
  Test in the L1Calo system during shutdown
  Fabricate and assemble full set of CMX modules
Notes: 11

## Slide 13: Conclusions
Schedule proposed is maintained
  Minor adjustments
Tasks proceeding according to plan
Need more detailed set of steps for in-situ tests before and after first beam
Optimistic outlook for project completion