## Slide 1
Status and planning of the CMX
Philippe Laurens for the MSU group
Level-1 Calorimeter Trigger General Meeting, CERN
May 24, 2012

## Slide 2: CMX: CMM upgrade
CMX replaces CMM:
JEM/CPM to CMX (backpl) rate 40 →160Mbps
Crate CMX to System CMX (cables) rate 40 →160Mbps
Cluster information sent to Topological Processor (12-fiber ribbons @6.4Gbps)
Optional partial TP capability included
  Standalone TP is now planned
  Some TP capability still desired for CMX platform (flexibility)

## Slide 3: The CMX overview
VME-- Interface
TP-CMX FPGA
Virtex-6
LX550T-FF1759
Base-CMX FPGA
Virtex-6
LX550T-FF1759
12x Optic OUT
12x Optic OUT
12x Optic IN
12x Optic IN
12x Optic IN
DAQ
ROI
DAQ
ROI
TCM Interface
VME--
TCM
Inputs from all
JEM or CPM
processors
from this crate
LVDS cables
From Crate
To System CMX
400 single ended
@ 160Mbps
3x27 LVDS pairs
@ up to 160 Mbps
2x 12-fiber
ribbons OUT
3x 12-fiber
ribbons IN
6.4 Gbps outputs
to Standalone TP
and/or TP-CMX
2x G-Link Out
2x G-Link Out
6.4 Gbps inputs
re-bundled from
up to 12 Base-CMX
CTP output
2x33 LVDS pairs
@ 40 Mbps
(from TP-CMX
via Base-CMX)

## Slide 4: CMX: modular design, most cards assembled without TP functionality
VME-- Interface
Base-CMX FPGA
Virtex-6
LX550T-FF1759
12x Optic OUT
12x Optic OUT
DAQ
ROI
TCM Interface
VME--
TCM
Inputs from all
JEM or CPM
processors
from this crate
LVDS cables
From Crate
To System CMX
400 single ended
@ 160Mbps
3x27 LVDS pairs
@ up to 160 Mbps
2x 12-fiber
ribbons OUT
6.4 Gbps outputs
to Standalone TP
and/or TP-CMX
2x G-Link Out
CTP output
2x33 LVDS pairs
@ 40 Mbps
(System CMX
only)

## Slide 5: CMX: Use scenario with standalone TP
Electron
Energy
Jet
Tau
Base-
CMX
FPGA
to CTP
LVDS
Cables
to CTP
to CTP
to CTP
Base-
CMX
FPGA
Base-
CMX
FPGA
Base-
CMX
FPGA
Base-
CMX
FPGA
Base-
CMX
FPGA
Base-
CMX
FPGA
Base-
CMX
FPGA
Base-
CMX
FPGA
Base-
CMX
FPGA
Base-
CMX
FPGA
Base-
CMX
FPGA
LVDS
Cables
LVDS
Cables
LVDS
Cables
Optical
Patch
Panel
Crate
CMXs
System
CMXs
- - - - - - - -
to CTP
Standalone
Topological
Processor
N x 12
12 x 12-fiber ribbons
12
1 x 12-fiber ribbon

## Slide 6: CMX development work on 3 fronts
3 parallel efforts
  CMX Engineering @MSU
    Philippe, Dan, and Chip
  CMX input module firmware @CERN
    Wojtek and Yuri
  VME/ACE/TTC (VAT) interface @CERN
    Yuri
CMX development schedule from Stockholm Preliminary Design Review is still valid
  Minor adjustments
Notes: 5

## Slide 7: CMX development schedule from PDR
2011: Project and engineering specifications
  CMX project Preliminary Design Review (done)
  Preliminary engineering design studies (done, RAL review)
  Test rig installed, checked out at MSU (postponed until 2012)
2012: Prototype design and fabrication
  CMX schematics and PCB layout (ongoing)
  CMM firmware ported to CMX
  Prototype fabrication (fall 2012)
  Basic tests for backward compatibility in test rig at MSU
  Production Readiness Review
2013: Prototype testing/installation/commissioning, final CMX fabrication
  Full prototype tests in test rig at CERN
  CMX firmware development and test
  Test in the L1Calo system during shutdown
  Fabricate and assemble full set of Final CMX (bulk with just Base, few with TP)
2014: Final commissioning in the L1Calo trigger system in USA15
Notes: 6

## Slide 8
CMX development timeline

## Slide 9: 2012
2012: Prototype design and fabrication
  CMX schematics and PCB layout
    CMX technology choice with Dual FPGA design: Base-CMX & TP-CMX (RAL Feb 2012)
    6U VME test card for VAT interface (PCB ready for testing in June)
    Real-time data path layout (ongoing)
    CMX input module firmware currently under test on the XILINX development module
    Power budget estimate
  Prototype fabrication
    mechanical testing
      Blank card, backplane connectors, front panel tests.
      Will happen before real prototype board, but not urgent yet.
  CMM firmware ported on CMX
    Firmware for VAT interface (2 CPLD + TTC FPGA) to Spartan-3AN FPGA (Adapt VHDL code, create test bench, specify VME register model) (Yuri)
    Most of CMM data path work completed at Stockholm (Pawel Plucinski, Sam Silverstein)
      Needs to be adapted to final package choice
  Basic tests for backward compatibility in test rig at MSU
  Production Readiness Review (L1Calo/TDAQ) Fall/Winter
    PRR after the prototype(s) is tested and
    final check before going into full production of final modules
Notes: 8

## Slide 10
2012: PCB layout: VME/ACE/TTC (VAT) interface test card
VME/ACE/TTC (VAT) part of CMM
Redesign HW with new components
    Fit design into single device
6U VME test card for
  Hardware implementation
  Main FPGA re-configuration
  Software
  To be merged into CMX design
PCB arrives in June
Next:
  Firmware for VAT card
  Firmware for Virtex 6 FPGA
  Test Stand and software
VME CPLD
TTC FPGA
ACE CPLD
SystemACE
TTCrx
FC
TTCDec
Spartan-3AN
VME-- logic
CF
SystemACE
JTAG
TTC
Connector for CANbus i/f
Virtex6
Power
5V0
3V3
2V5
1V0
3V3
2V5
1V0
1V2

## Slide 11: 2011/2012: design studies: Clock/parity recovery
Clock+Parity encoded on single line
Variable duty cycle
Setup:
Scheme tested using Virtex 6 eval board
Data capture developed, simulated and ‘Placed and Routed’ on target FPGA
  Needs repeating – different package chosen
Clock/parity
Regional clock buffer (BUFR)
MMCM
Data
40 MHz
BUFR
80 MHz
BUFIO
IDDR
40MHz register
96 bits @ 40MHz
x 16

## Slide 12: 2012 PCB Layout: Backplane – FPGA connection
Optimize Real-Time Path Layout
  High local density near FPGA
  Especially 400x JEM/CPM inputs
  Spread out & mixed up on backpln  grouped & sorted at FPGA
  Span neighbor IO blocks
  Regional Clock input for clock/parity
  Tune IO Assignments
  Cleanest connections: no extra via
  Minimize number of trace layers
NOT FINAL
In Parallel with Firmware design
  Validate assignment
  Timing constraints

## Slide 13: Conclusions
Original schedule is maintained
  With minor adjustments
  Prototype effort proceeding in parallel on 3 fronts according to plan
  Will need to increase level of detail for set of steps during in-situ tests before and after first beam
Optimistic outlook